## Sheet1
Báo cáo tổng hợp tiến độ thực hiện Khóa luận tốt nghiệp Fall 2023
Giảng viên: | M.S. Trung Nguyen Quoc
Bộ môn: | Artificial intelligence
Code | Topic | Lịch hẹn SV | Tiến độ thực hiện
|  | (giờ-ngày trong tuần) | Tuần 1 | Tuần 2 | Tuần 3 | Tuần 4 | Tuần 5 | Tuần 6 | Tuần 7 | Tuần 8 | Tuần 9 | Tuần 10 | Tuần 11 | Tuần 12 | Tuần 13 | Tuần 14
FA23AI23 | Symbolic Dialouge for General Domain State Tracking | Slot 6, Tuesday, weekly | Review concepts TOD and symbolic methods | Review related works and select datasets and models | Brainstorm ideas for experiments | Develop code for dataset handler and train initial experiments | Evaluate results of initial experiments | Review experiment 1 and brainstorm new experiments | Develop code and dataset handlers for experiment 2 Train experiment 2 | Evaluate the results of the second experiments | First draft of the paper and final review and finalize the results | Finalize papers | Conduct final review and finalize results Finalize paper | Write report Process paper submission | _Process paper submission Review Report | _Revision and improvements
Tuần 1: | Phê duyệt KH chi tiết thực hiện khóa luận, supervisor phê duyệt
Tuần 13: | Phê duyệt bảo vệ khóa luận: supervisor đề nghị, CNBM xem xét và phê duyệt
- Fail: toàn bộ nhóm
- OK, với danh sách SV (có thể có SV không được bảo vệ)

## Sheet2
Báo cáo chi tiết
Code: | FA23AI23
Topic: | Symbolic Dialouge for General Domain State Tracking
MSSV | Họ tên SV | Phân công |  |  |  | Tiến độ thực hiện
|  | Nhiệm vụ 1 | Nhiệm vụ 2 | Nhiệm vụ 3 | Nhiệm vụ 4 | Tuần 1 | Tuần 2 | Tuần 3 | Tuần 4 | Tuần 5 | Tuần 6 | Tuần 7 | Tuần 8 | Tuần 9 | Tuần 10 | Tuần 11 | Tuần 12 | Tuần 13 | Tuần 14
SE160997 | Nguyễn Sơn Tùng | Select model and dataset | Implementation experiences | write and submit papers |  | Conduct a thorough review of relevant concepts related to TOD and symbolic methods. | Conduct a thorough review of relevant concepts related to TOD and symbolic methods. | Conduct a thorough review of relevant concepts related to TOD and symbolic methods. | Review existing research related to symbolic dialogue for general domain state tracking and identify suitable datasets and models. | Collaboratively select appropriate models for the project, considering factors such as model complexity, performance, and compatibility with the chosen datasets. Optimize hyperparameters for the selected models to enhance their performance. | Collaboratively select appropriate models for the project, considering factors such as model complexity, performance, and compatibility with the chosen datasets. Optimize hyperparameters for the selected models to enhance their performance. |  |  | Analyze the experimental results obtained from the trained models, evaluating their performance metrics, identifying patterns, and drawing meaningful conclusions. | Analyze the experimental results obtained from the trained models, evaluating their performance metrics, identifying patterns, and drawing meaningful conclusions. | Design an ablation study to identify the key components that contribute most significantly to the performance of the selected models. | Execute the ablation study by systematically removing or modifying specific components of the models, observing the impact on their performance.
SE160773 | Nguyễn Mạnh Tường | Coordinate between internal team and external team | Resource management( hardware + software) | Write test and evaluate models performance |  | Conduct a thorough review of relevant concepts related to TOD and symbolic methods. | Conduct a thorough review of relevant concepts related to TOD and symbolic methods. | Conduct a thorough review of relevant concepts related to TOD and symbolic methods. |  | Collaboratively select appropriate models for the project, considering factors such as model complexity, performance, and compatibility with the chosen datasets. Optimize hyperparameters for the selected models to enhance their performance. | Collaboratively select appropriate models for the project, considering factors such as model complexity, performance, and compatibility with the chosen datasets. Optimize hyperparameters for the selected models to enhance their performance. |  |  | Analyze the experimental results obtained from the trained models, evaluating their performance metrics, identifying patterns, and drawing meaningful conclusions. | Analyze the experimental results obtained from the trained models, evaluating their performance metrics, identifying patterns, and drawing meaningful conclusions. |  | Execute the ablation study by systematically removing or modifying specific components of the models, observing the impact on their performance. | Analyze the results of the ablation study, assessing the contribution of each component to the overall performance of the models.
SE160753 | Lê Xuân Tùng | Review models and datasets | Implementation experiences | write and submit reports( weekly and final) |  | Conduct a thorough review of relevant concepts related to TOD and symbolic methods. | Conduct a thorough review of relevant concepts related to TOD and symbolic methods. | Conduct a thorough review of relevant concepts related to TOD and symbolic methods. |  |  |  | Implement the training procedures for the selected models, ensuring proper data preparation and model configuration. Conduct experiments to evaluate the performance of the trained models under various conditions. | Implement the training procedures for the selected models, ensuring proper data preparation and model configuration. Conduct experiments to evaluate the performance of the trained models under various conditions. | Analyze the experimental results obtained from the trained models, evaluating their performance metrics, identifying patterns, and drawing meaningful conclusions. | Analyze the experimental results obtained from the trained models, evaluating their performance metrics, identifying patterns, and drawing meaningful conclusions. |  | Execute the ablation study by systematically removing or modifying specific components of the models, observing the impact on their performance. |  | Based on the findings of the ablation study, refine the model architecture and hyperparameters to improve performance. Evaluate the refined models to assess the effectiveness of the improvements.